## Sheet1
Project: Dynamic App Server: https://dev.azure.com/caresoft-sw Query: Sprint-9 planning List type: Flat
ID | Work Item Type | Title | Assigned To | State | Original Estimate | Dev Start date | Completed Work | Remaining Work | Development Target | QA Original Estimate | QA Target | QA Completed | QA Remaining | Tentative UAT
3170 | Task | Excel export - Row/Cell color based on logic | Aravindraj Sekar | QA Deployment | 15 | 2023-09-13 | 6 | 9 | 2023-09-20
3171 | Task | Manage Guideline marquee text | Arunbalaji Sundaram | Development | 37 | 2023-09-08 | 78.5 | -41.5 | 2023-09-21 | 7 | 2023-10-03 | 1 | 6
3424 | Task | Unique code creation for Tenant Name | Deepak Ramasamy | QA Deployment | 8 | 2023-09-25 | 9 | -1 | 2023-09-26
3121 | Task | Show location below User name | Deepak Ramasamy | QA Deployment | 17 | 2023-09-06 | 13.7 | 3.3 | 2023-09-11 | 5 | 2023-09-27 | 1 | 4
944 | Task | Data Base project creation to streamline the SQL script deployment | Jebathurai Muthupandi | Development | 20 | 2023-08-08 | 18 | 2 | 2023-08-09 |  |  |  |  | 2023-09-08
2715 | Task | DynamicApp Local DB Clean Up | Jebathurai Muthupandi | Closed | 8 | 2023-08-10 | 7 |  | 2023-08-14 |  |  |  |  | 2023-09-06
3169 | Task | Customer Summary email | Jebathurai Muthupandi | Development | 13 | 2023-09-19 | 8 | 5 | 2023-09-25
3126 | Task | Cascade date info to Child/Parent | Kranthi Kukudala | Development | 33 | 2023-09-13 | 8 | 25 | 2023-09-19 | 12 | 2023-10-06
3130 | Task | Service type wise TS entry option | Kranthi Kukudala | QA Deployment | 10 | 2023-09-06 | 8 | 2 | 2023-09-08 | 5 | 2023-10-11
3529 | Task | Project ID fetch from Timesheet Table in Edit Time sheet Popup | Kranthi Kukudala | Development | 8 | 2023-09-29
1499 | Task | Form Master & Page master grid view UI updates | Muthuraj Ponnusamy | Development | 20 | 2023-06-12 | 31 | -11 | 2023-06-21 | 6 | 2023-08-23 | 1 | 5 | 2023-08-31
1794 | Task | Dynamic Master Page UI Modification | Muthuraj Ponnusamy | Development | 16 | 2023-08-07 | 19.5 | -3.5 | 2023-08-08 | 5 | 2023-08-11 | 1 | 4 | 2023-08-31
1125 | Task | Table Partition analysis to overcome Archival Process | Raja Sekar | System Testing | 15.5 | 2023-08-17 | 12 | 3.5 | 2023-08-25 | 7 | 2023-08-29 | 4 | 3 | 2023-08-31
2717 | Task | Data closure for Archival Process | Raja Sekar | Development | 8 | 2023-09-01 | 4 | 4 | 2023-09-06 |  |  |  |  | 2023-09-29
2718 | Task | Auto Workflow selection depending on Release type | Sandhya Velu | Development | 32 | 2023-09-06 | 48 | 16 | 2023-09-12 | 20 | 2023-09-18
3159 | Task | To display unique count on completion stage | Saravanan Arumugam | Closed | 16 | 2023-09-08 | 15.3 |  | 2023-09-13 | 7 | 2023-09-21 | 3 | 4
2490 | Task | Convert hard delete to soft delete for entire application | Sowntharya Rangaraj | QA Deployment | 44 | 2023-08-16 | 66.5 | -26.5 | 2023-08-23 | 14 | 2023-08-28 | 1 | 13 | 2023-08-31
3118 | Task | Feedback provision for Customer | Sowntharya Rangaraj | Development | 30 | 2023-09-11 | 18 | 12 | 2023-09-15 | 10 | 2023-09-29 | 1 | 9
2833 | Task | Introduce order by for Global filter | Surya Chandrasekaran | Closed | 20 | 2023-09-05 | 23 |  | 2023-09-11 | 9 | 2023-09-15
3127 | Task | Attachment upload from Summary page | Surya Chandrasekaran | Unit Testing | 26 | 2023-09-12 | 42.5 | -16.5 | 2023-09-21 | 10 | 2023-09-28 | 2 | 8
3636 | Task | Production Site Issue Maintenance |  | New

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | 2023-09-20 | value doesn't matter | \ | \ | Select User... | Closed | Select User... | Active | Select User... | Active | Select User... | Active | Select User... | Closed | Select User... | Closed | Select User... | Active | Bug | Select User... | Closed | Select User... | Closed
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd-MM-yyyy HH:mm | readOnlyTestRange_General | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_System.AreaPath | \Sprint 1 | Adnan Gayaz | Development | Adnan Gayaz | Closed | Adnan Gayaz | Closed | Adnan Gayaz | Closed | Adnan Gayaz | Development | Adnan Gayaz | Design | Adnan Gayaz | Closed | Epic | Adnan Gayaz | Development | Adnan Gayaz | Development
[5 empty] | \Sprint 10 | Ajeeth Duraisamy | In-Valid | Ajeeth Duraisamy | New | Ajeeth Duraisamy | New | Ajeeth Duraisamy | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Issue_System.State | Ajeeth Duraisamy | Live Deployment | Ajeeth Duraisamy | Ready | Ajeeth Duraisamy | New | Feature | Ajeeth Duraisamy | In-Valid | Ajeeth Duraisamy | Live Deployment
[5 empty] | \Sprint 2 | Aravindraj Sekar | Live Deployment | Aravindraj Sekar | Removed | Aravindraj Sekar | Removed | Aravindraj Sekar |  | Aravindraj Sekar | New | Aravindraj Sekar | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Test Case_System.State | Aravindraj Sekar | Removed | Issue | Aravindraj Sekar | Live Deployment | Aravindraj Sekar | New
[5 empty] | \Sprint 3 | Arunbalaji Sundaram | New | Arunbalaji Sundaram | Resolved | Arunbalaji Sundaram | Resolved | Arunbalaji Sundaram |  | Arunbalaji Sundaram | On-hold | Arunbalaji Sundaram |  | Arunbalaji Sundaram | Resolved | Task | Arunbalaji Sundaram | New | Arunbalaji Sundaram | On-hold
[5 empty] | \Sprint 4 | Deepak Ramasamy | QA Deployment | Deepak Ramasamy | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Epic_System.State | Deepak Ramasamy | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Feature_System.State | Deepak Ramasamy |  | Deepak Ramasamy | QA Deployment | Deepak Ramasamy |  | Deepak Ramasamy | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_User Story_System.State | Test Case | Deepak Ramasamy | QA Deployment | Deepak Ramasamy | QA Deployment
[5 empty] | \Sprint 5 | Ezhilkumar Sankar | Re-Open (QA) | Ezhilkumar Sankar |  | Ezhilkumar Sankar |  | Ezhilkumar Sankar |  | Ezhilkumar Sankar | Removed | Ezhilkumar Sankar |  | Ezhilkumar Sankar |  | User Story | Ezhilkumar Sankar | Re-Open (QA) | Ezhilkumar Sankar | Removed
[5 empty] | \Sprint 6 | Gowtham Kumaravel | Re-Open (UA) | Gowtham Kumaravel |  | Gowtham Kumaravel |  | Gowtham Kumaravel |  | Gowtham Kumaravel | Requirement Analysis and Estimation | Gowtham Kumaravel |  | Gowtham Kumaravel |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_System.WorkItemType | Gowtham Kumaravel | Re-Open (UA) | Gowtham Kumaravel | Requirement Analysis and Estimation
[5 empty] | \Sprint 7 | Jebathurai Muthupandi | Required Clarification | Jebathurai Muthupandi |  | Jebathurai Muthupandi |  | Jebathurai Muthupandi |  | Jebathurai Muthupandi | Re-Work (QA) | Jebathurai Muthupandi |  | Jebathurai Muthupandi |  |  | Jebathurai Muthupandi | Required Clarification | Jebathurai Muthupandi | Re-Work (QA)
[5 empty] | \Sprint 8 | Kranthi Kukudala | To be validated QA | Kranthi Kukudala |  | Kranthi Kukudala |  | Kranthi Kukudala |  | Kranthi Kukudala | Re-Work (UA) | Kranthi Kukudala |  | Kranthi Kukudala |  |  | Kranthi Kukudala | To be validated QA | Kranthi Kukudala | Re-Work (UA)
[5 empty] | \Sprint 9 | Manikandan Radhakrishnan | To be validated UA | Manikandan Radhakrishnan |  | Manikandan Radhakrishnan |  | Manikandan Radhakrishnan |  | Manikandan Radhakrishnan | System Testing | Manikandan Radhakrishnan |  | Manikandan Radhakrishnan |  |  | Manikandan Radhakrishnan | To be validated UA | Manikandan Radhakrishnan | System Testing
[5 empty] | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_System.IterationPath | Mohamedameen Yousuf | UA Deployment | Mohamedameen Yousuf |  | Mohamedameen Yousuf |  | Mohamedameen Yousuf |  | Mohamedameen Yousuf | UA Deployment | Mohamedameen Yousuf |  | Mohamedameen Yousuf |  |  | Mohamedameen Yousuf | UA Deployment | Mohamedameen Yousuf | UA Deployment
[6 empty] | Muthuraj Ponnusamy | Unit Testing | Muthuraj Ponnusamy |  | Muthuraj Ponnusamy |  | Muthuraj Ponnusamy |  | Muthuraj Ponnusamy | UAT | Muthuraj Ponnusamy |  | Muthuraj Ponnusamy |  |  | Muthuraj Ponnusamy | Unit Testing | Muthuraj Ponnusamy | UAT
[6 empty] | Mythili Santhanam | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Bug_System.State | Mythili Santhanam |  | Mythili Santhanam |  | Mythili Santhanam |  | Mythili Santhanam | Unit Testing | Mythili Santhanam |  | Mythili Santhanam |  |  | Mythili Santhanam | Active | Mythili Santhanam | Unit Testing
[6 empty] | Pradeep Sathiyanarayanan |  | Pradeep Sathiyanarayanan |  | Pradeep Sathiyanarayanan |  | Pradeep Sathiyanarayanan |  | Pradeep Sathiyanarayanan | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Task_System.State | Pradeep Sathiyanarayanan |  | Pradeep Sathiyanarayanan |  |  | Pradeep Sathiyanarayanan | Removed | Pradeep Sathiyanarayanan | VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_E9-FF-87-2B-2E-30-A4-C6-6B-63-60-6E-DF-8C-F8-55-1C-E3-C3-14
[6 empty] | Ragul Rajaannamalai |  | Ragul Rajaannamalai |  | Ragul Rajaannamalai |  | Ragul Rajaannamalai |  | Ragul Rajaannamalai |  | Ragul Rajaannamalai |  | Ragul Rajaannamalai |  |  | Ragul Rajaannamalai | Resolved | Ragul Rajaannamalai
[6 empty] | Raja Sekar |  | Raja Sekar |  | Raja Sekar |  | Raja Sekar |  | Raja Sekar |  | Raja Sekar |  | Raja Sekar |  |  | Raja Sekar | On-hold | Raja Sekar
[6 empty] | Ramkumar Muthu |  | Ramkumar Muthu |  | Ramkumar Muthu |  | Ramkumar Muthu |  | Ramkumar Muthu |  | Ramkumar Muthu |  | Ramkumar Muthu |  |  | Ramkumar Muthu | Requirement Analysis and Estimation | Ramkumar Muthu
[6 empty] | Ramya Elango |  | Ramya Elango |  | Ramya Elango |  | Ramya Elango |  | Ramya Elango |  | Ramya Elango |  | Ramya Elango |  |  | Ramya Elango | Re-Work (QA) | Ramya Elango
[6 empty] | Sandhya Velu |  | Sandhya Velu |  | Sandhya Velu |  | Sandhya Velu |  | Sandhya Velu |  | Sandhya Velu |  | Sandhya Velu |  |  | Sandhya Velu | Re-Work (UA) | Sandhya Velu
[6 empty] | Saravanan Arumugam |  | Saravanan Arumugam |  | Saravanan Arumugam |  | Saravanan Arumugam |  | Saravanan Arumugam |  | Saravanan Arumugam |  | Saravanan Arumugam |  |  | Saravanan Arumugam | System Testing | Saravanan Arumugam
[6 empty] | Sasikala Thelaganaboyina |  | Sasikala Thelaganaboyina |  | Sasikala Thelaganaboyina |  | Sasikala Thelaganaboyina |  | Sasikala Thelaganaboyina |  | Sasikala Thelaganaboyina |  | Sasikala Thelaganaboyina |  |  | Sasikala Thelaganaboyina | UAT | Sasikala Thelaganaboyina
[6 empty] | Sowntharya Rangaraj |  | Sowntharya Rangaraj |  | Sowntharya Rangaraj |  | Sowntharya Rangaraj |  | Sowntharya Rangaraj |  | Sowntharya Rangaraj |  | Sowntharya Rangaraj |  |  | Sowntharya Rangaraj | Design | Sowntharya Rangaraj
[6 empty] | Suresh Lingamurthy |  | Suresh Lingamurthy |  | Suresh Lingamurthy |  | Suresh Lingamurthy |  | Suresh Lingamurthy |  | Suresh Lingamurthy |  | Suresh Lingamurthy |  |  | Suresh Lingamurthy | Ready | Suresh Lingamurthy
[6 empty] | Surya Chandrasekaran |  | Surya Chandrasekaran |  | Surya Chandrasekaran |  | Surya Chandrasekaran |  | Surya Chandrasekaran |  | Surya Chandrasekaran |  | Surya Chandrasekaran |  |  | Surya Chandrasekaran | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_System.State | Surya Chandrasekaran
[6 empty] | Thenmozhi Elangovan |  | Thenmozhi Elangovan |  | Thenmozhi Elangovan |  | Thenmozhi Elangovan |  | Thenmozhi Elangovan |  | Thenmozhi Elangovan |  | Thenmozhi Elangovan |  |  | Thenmozhi Elangovan |  | Thenmozhi Elangovan
[6 empty] | Vijaybalaji Senthilkumar |  | Vijaybalaji Senthilkumar |  | Vijaybalaji Senthilkumar |  | Vijaybalaji Senthilkumar |  | Vijaybalaji Senthilkumar |  | Vijaybalaji Senthilkumar |  | Vijaybalaji Senthilkumar |  |  | Vijaybalaji Senthilkumar |  | Vijaybalaji Senthilkumar
[6 empty] | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Bug_System.AssignedTo |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Epic_System.AssignedTo |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Feature_System.AssignedTo |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Issue_System.AssignedTo |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Task_System.AssignedTo |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_Test Case_System.AssignedTo |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_User Story_System.AssignedTo |  |  | all_VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_System.AssignedTo |  | VSTS_de064e54_75b4_4039_9954_0d34ebc733e7_49-44-46-70-89-80-38-2B-91-FB-90-F9-34-DA-24-C1-F3-45-21-58